## Slide 1: Establishing a “Sustainability” Commission
Lessons Learned
(based on our experience in Bloomington)

## Slide 2: Agenda
Get to know where your council / mayor / city manager stands
Assemble a “Task Force”
Interview Other Active Commissions
Consolidate Information / Design Your Commission
Review with key stakeholders / Update
Work with Key Stakeholders to Strategize Approval
Where we are Today / Comp Plan

## Slide 3: Get to Know Key Stakeholders
Council Members
Mayor
City Manager
Where do they stand, what are their concerns, what questions do they have?
Is there a champion?

## Slide 4: Assemble a Task Force
Sanctioned? Not Sanctioned?
Focus is:
  Why – Benefit to the city
  What – How structured
  How – How would it operate
Select Members Carefully
  Have Time / Will Show Up
  Project Management
  Sustainability Expertise
  Commission Expertise
  Potential Commission Members / Work Well in a group
  Passion
  Council Members? / City Staff?

## Slide 5: Interview Active Sustainability Commissions
Commission
Liaison (separately)
How are They Structured
  Scope,
  #,
  Workgroups?,
  etc.)
Lessons Learned
Advice

## Slide 6: Keep Stakeholders Informed
What are You Learning?
What are Your Next Steps?
What Direction are You Headed?

## Slide 7: Vision / Design
Why – What’s the Benefit
What:
  What’s the Scope
  How structured / Processes?
    How many members?
    Any membership requirements / “role holders”?
    How will it interact with the community?
  Recommendation on Liaison.
  Etc.
Review with Key Stakeholders & Update. Get Buy-In
Write a Draft Ordinance

## Slide 8: Strategize and Get Approval
Work with Your Champion(s)
Get the Mayor On Board
Shore-up Supporters
Try to Bring over those Opposed
Determine who’s going to “Call the Question”

## Slide 9: Where we Are Today
Nine Members
  5 must have expertise in one or more areas of sustainability
  1 City Council Member
Staff Liaison – Dpty Dir. Public Works
One Work Group for Each Area:
  Energy / Carbon
  Solid Waste
  Surface / Ground Water
  Ecological Land Stewardship

## Slide 10: Major Initiatives
Kick-off Meeting in March 2017 – Established 2017 Work Plan
Green Step City
Partners in Energy (PIE) – city wide energy conservation plan
Organics Drop Off
Review 10 Year Watershed District Plans
Identify Measures for Each Area
Establish Long Term Goals (for each area)

## Slide 11: Comp Plan
Work with Planning Dept.
Ensure Proper Emphasis on Areas Aspects of Sustainability
Specific Long Term Goals will come Later